## Implementation Plan
PRODUCTION DEPLOYMENT – ADO PIPELINE IMPLEMENTATION PLAN
Estimated Total Window · Best Case: ~4 hrs 10 min ¦ Worst Case: ~6 hrs 15 min
# | Task / Activity | Detail / Sub-steps | Est. Duration (min) | Cumulative Time (min) | Start (T+ min) | End (T+ min) | Parallelism | Dependencies / Risks
1 | Stop Frontline Routers | Graceful shutdown of all frontline router instances via ADO pipeline | 15 | 15 | 0 | 15 | Serial | All downstream deployments depend on this step
2 | DDL Pipeline Deployment | Execute DDL migration scripts; schema changes applied to target DBs | 20–30 | 45 | 15 | 45 | Serial | Must complete before any pipeline deployments
3 | Postgres Pipeline Deployments (×15) | Deploy each of the 15 Postgres pipelines sequentially ~10–15 min each | 150–225 | 270 | 45 | 270 | Serial – NO parallel | Certificate dependencies; run one at a time
4 | Oracle Pipeline Deployments (×8) | Deploy each of the 8 Oracle pipelines sequentially ~5–10 min each | 40–80 | 350 | 270 | 350 | Serial – NO parallel | Must follow Postgres deployments
4P | Topic Alter | Run Kafka/topic alter scripts in parallel while DB pipelines (Step 3/4) execute | 30–45 |  | 35 | 80 | ✔ PARALLEL with Step 3 & 4 | Can run concurrently; monitor for conflicts
5 | Source Pipeline Deployments (×3) | Deploy 3 source pipelines sequentially ~60 min each | 180 | 530 | 350 | 530 | Serial – NO parallel | Certificate dependency prevents parallel execution
6 | Verification, Closure & Confirmation | Smoke tests, data-flow checks, sign-off from leads | 15–20 | 550 | 530 | 550 | Serial | All pipelines must be healthy before sign-off
7 | Start Frontline Routers | Bring frontline router instances back online via ADO pipeline | 10 | 560 | 550 | 560 | Serial | Routers must start only after full verification
8 | Log Verification | Review deployment logs, error rates, and pipeline metrics | 20–30 | 590 | 560 | 590 | Serial | Final health check before deployment closure
TOTAL ESTIMATED MAINTENANCE WINDOW |  |  | Best: 250 min Worst: 420 min | ⚠ Topic Alter (Step 4P) runs in parallel with Postgres & Oracle deployments — it does NOT add to the critical path. Source Pipelines (Step 5) are the longest serial block.
LEGEND
| Parallel task (non-critical path) |  | Serial task step # |  | Dependency / caution |  | Summary total

## Timeline Summary
DEPLOYMENT TIMELINE SUMMARY – Critical Path vs. Parallel Activities
# | Activity | Best (min) | Worst (min) | Cumulative Best (min) | Cumulative Worst (min) | Notes
1 | Stop Frontline Routers | 15 | 15 | 15 | 15 | Critical path start
2 | DDL Pipeline Deployment | 20 | 30 | 35 | 45 | Blocking step
3 | Postgres Pipelines (×15 serial) | 150 | 225 | 185 | 270 | Longest Postgres block
4P | Topic Alter ← PARALLEL → | 30 | 45 | – | – | Runs during Step 3; non-critical
4 | Oracle Pipelines (×8 serial) | 40 | 80 | 225 | 350
5 | Source Pipelines (×3 serial) | 180 | 180 | 405 | 530 | Cert dependency – no parallelism
6 | Verification & Sign-off | 15 | 20 | 420 | 550
7 | Start Frontline Routers | 10 | 10 | 430 | 560
8 | Log Verification | 20 | 30 | 450 | 590 | Final closure
TOTAL WINDOW |  | 250 | 590 | 250 | 590 | Topic Alter runs in parallel – not on critical path